## from LSUHSC
Grants Transfer From LSUHSC-NO Events Checklist
EVENT | ACTION TO BE TAKEN | DAYS BEFORE MOVE | ACTION TAKEN BY
1 | Notify Sponsored Projects | 122 | Investigator
2 | Notify Asset Management of intent to transfer equipment | 122 | Investigator
3 | Asset Management develops list of assets by grant/project#. | 118 | Asset Management
4 | Provide list of of assets to Department and Sponsored Projects that is part of grant that is to be transferred. List is to include any supplies and items not tagged (proof that items not tagged were purchased with grant funds will be required.) Final approval of the transfer of equipment resides with the Department and Sponsored Projects. | 113 | Investigator
5 | Prepare forms, letters, and notices. Any special instructions regarding equipment should be forwarded to Asset Management. | 108 | Investigator
6 | Complete forms required by contract terms (ie. PHS 3734 - Official Statement Relinquishing Interests and Rights in Public Health Service Grant) and turn in to Sponsored Projects Administration for review. | 103 | Investigator
7 | Sponsored Projects Administration reviews all forms, letters, and notices provided to them. | 100 | Sponsored Projects
8 | Forward all approval documentation to transfer grants to Asset Management. | 90 | Investigator
9 | Request authorization from Louisiana Property Assistance Agency (LPAA) to remove assets from inventory of LSUHSC-NO based on assets identified on grant transfer. | 90 | Asset Management
10 | Receive approval from LPAA and notify Investigator. | 45 | Asset Management
11 | Schedule final pickup of assets with moving company (if necessary). | 30 | Investigator
12 | Pack equipment | 30 | Investigator
13 | Move date | 0 | Investigator
1) Under current state law, at the conclusion of a grant the title for equipment reverts to the state. When the equipment is no longer any use to the Health Science Center, it is sent to LPAA for either transfer to another state agency as needed or sent to public auction. Exceptions to this regulation in individual instances require written approval from LPAA as promulgated by Title 34, Part VII S505 B2. An example of an acceptable exception might be a written document, from the inception of acquisition, stating the equipment was purchased or donated with a specific intent to remain with a researcher, etc. The LPAA will make a decision determined to be in the best economical interest of the state. Please note in order to pursue an exception we would need specific information and records to support the request.

## to LSUHSC
Grants Transfer To LSUHSC-NO Events Checklist
EVENT | ACTION TO BE TAKEN | ACTION TAKEN BY
1 | Notification that grant is transferring to LSUHSC-NO. Investigator should check with Sponsored Projects and Purchasing to facilitate transfer. | Investigator
2 | Notification and approval by transferring Institution of equipment transferred including original cost, original acquisition date, accumulated depreciation, and a description of the equipment. A copy should be forwarded to Sponsored Projects Administration and Asset Management. | Investigator
3 | Purchasing will notify Asset Management of any scheduled movement of equipment by a moving company to be transferred on-campus. | Purchasing
4 | Notify Asset Management of equipment's arrival on-campus | Investigator
5 | Tag equipment | Asset Management